## Sheet1
Schedule
Project Name: Alarm Clock
ID | Item | Person | Working Hours |  | Process | Start Day | End Day | Over Day1 | Over Day2
1 | Research Android Operation System | S.Anh | Plan |  | 50% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
2 | Stored media files in Android | S.Anh | Plan |  | 50% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
3 | Research android.app.AlarmManager object for Alarm Clock configuration | Duoc | Plan |  | 0% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
4 | Research for how to set schedule times in Android | Duoc | Plan |  | 0% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
5 | Research for how to record video/audio in Android | Hieu | Plan |  | 0% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
6 | How to use SQLite in Android | Binh | Plan |  | 50% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
7 | Make schedule and system design (overview) | Duoc | Plan | 4 | 100% | 2011-10-09 | 2011-10-11 | 2011-11-06
|  |  | Actual | 4 | 100%
8 | Specialize Document | Nam | Plan |  | 0% | 2011-10-09 | 2011-10-21 | 2011-11-06
Actual
9 | Research for android project structure and android components | Duoc | Plan |  | 0% | 2011-10-09 | 2011-10-22 | 2011-11-06
Actual